## Memory+Interrupts
				There may be a reason not to use addr 1111
	A23	A22	A21	A20	MODE				Interrupts	IPL2	IPL1	IPL0	Meaning
F	1	1	1	1	CPLD	N/A			7	1	1	1	Unmaskable
E	1	1	1	0	CPLD	Speaker 16-23			6	1	1	0
D	1	1	0	1	CPLD	Speaker 8-15			5	1	0	1
C	1	1	0	0	CPLD	Speaker 0-7			4	1	0	0
B	1	0	1	1	CPLD				3	0	1	1
A	1	0	1	0	CPLD				2	0	1	0
9	1	0	0	1	CPLD	GPIO 8-15			1	0	0	1
8	1	0	0	0	CPLD	GPIO 0-7			0	0	0	0
7	0	1	1	1
6	0	1	1	0
5	0	1	0	1
4	0	1	0	0
3	0	0	1	1	CPLD Masks	Enable/disable speaker, use data pins as interrupt vector, use data pins as buffer
2	0	0	1	0	DUART	A19-16 used for mode-setting
1	0	0	0	1	RAM
0	0	0	0	0	ROM

## Sheet1
Sheet 1: Parts list
Sheet 2: Supply requirements					MicroComputer Design
Sheet 3: Symbol/Pattern/Component Progress					Sample by Dr. kim
Sheet 4: Time Sheet
Sheet 5: Project Progress
Master Parts List
Item	Symbols	Quantity	Price(each)	Price(sum)	Description	Manufacturers Part Number		Website of Part
Processor		5	$2.26	$11.28	68000 CPU 20MHz, 64-pin PLCC	MC68HC000FN20	J	eBay
Sold Processor		1	$(2.00)	$(2.00)	CPU purchased by Brian
Processor Socket		2	$1.42	$2.84	CONN SOCKET PLCC 68POS TIN	AE10059-ND		digikey
CPU Oscillator		1	$2.37	$2.37	OSC XO 80.000MHZ TTL PC PIN	XC1194-ND		digikey
Oscillator Sockets		2	$0.25	$0.50	8-pin dip socket			supply closet
CPLD		2	$8.00	$16.00	IC CPLD 72 MCELL C-TEMP 84-PLCC	XC9572-7PC84C		eBay
CPLD Socket		5	$0.51	$2.56	5x PLCC IC Socket DIP 84 PINS PLCC-84	?		eBay
Jtag	6-pin	3	$0.68	$2.04	Headers & Wire Housings 16CKT VERT HDR	22-28-4161	m	http://www.mouser.com/Search/ProductDetail.aspx?qs=GAPJcf4kvdv3Xd3iPYTA6w%3d%3d
DUART		2	$5.00	$9.99	40-DIP	MC68681L		eBay
Duart Socket		1	$1.02	$1.02	CONN SOCKET PLCC 44POS TIN	AE10057-ND		digikey
Duart CLK		1	$1.88	$1.88	OSC 3.6864 MHZ 5.0V FULL SIZE	XC1158-ND		digikey
RS232 Driver		2	$1.37	$2.74	IC DUAL RS232 ESD-PROT 16-DIP 250kbps	MAX232EIN		digikey	Needs some 1uF caps
RS232 Driver Socket		1	$0.50	$0.50	16-pin dip socket			supply closet
D-Sub connector		1	$1.54	$1.54	CONN D-SUB PLUG 9POS R/A SOLDER	A109020-ND		digikey
Ram		2	$4.98	$9.96	IC SRAM 4MBIT 12NS 44SOJ	AS7C4098A-12JIN		digikey
Rom		4	$1.67	$6.68	IC FLASH 4MBIT 70NS 32DIP	SST39SF040-70-4C		digikey
Rom ZIF Socket		2	$2.49	$4.98	40Pin ZIF ZIP DIP			ebay
5v Regulator		1	$4.27	$4.27	IC REG LDO 5V 3A TO220-3	LT323AT		digikey
ON/OFF switch		2	$1.09	$2.18	Slide Switches MINI SLIDE SWITCH	SLA1200	m	mouser
Reset Button		2	$0.76	$1.52	SWITCH TACT 6MM SMD MOM 160GF	B3S-1000		http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=SW415-ND
LEDs		18	$0.31	$5.63	SMD 3.2X1.6MM LOW CRNT Blue	APT3216LVBC/D	m	http://www.mouser.com/Search/ProductDetail.aspx?qs=7JStj%2fjQ2SEA%252b%2fUbcPiheQ%3d%3d
Resistor 1.0k	Online	100	$0.01	$0.60	SMD 0805 1Kohms 5% AEC-Q200	ERJ-6GEYJ102V	m	mouser
Resistor 4.7k	Online	100	$0.01	$0.60	SMD 0805 4.7Kohms 5% AEC-Q200	ERJ-6GEYJ472V	m	mouser
Capacitor 1 uF	Online	35	$0.04	$1.33	MLCC - SMD/SMT 0805 1uF 16volts X5R 10%	GRM21BR61C105KA01L	m	mouser
Capacitor 22 uF 6.3V	Online	2	$0.24	$0.48	MLCC - SMD/SMT 0805 22uF 6.3volts X5R 20%	GRM21BR60J226ME39L	m	mouser
Capacitor 47 uF 25V		1	$0.99	$0.99	Ceramic Leaded 47uF 25volts X5R 20% Radial ThruHole	FG16X5R1E476MRT00	m	mouser
Barrel Plug (Male)		1	$0.85	$0.85	CONN PWR JACK 2.1X5.5MM SOLDER	EJ508A-ND		digikey
9V AC Adaptor		1	$6.59	$6.59	9V 2A 2000mA DC AC Adapter Charger	-		ebay
Logic Analyser		1	$6.79	$6.79
PCB Board		1	$33.00	$33.00
PCB Shipping and H		1	$10.00	$10.00
Digikey Shipping		1	$10.55	$10.55
Mouser Shipping+Tax		1	$7.77	$7.77
68000 Shipping		1	$2.00	$2.00
DUART Shipping		1	$2.50	$2.50
CPLD Shipping		1	$4.10	$4.10
84pin socket shipping		1	$1.85	$1.85
ZIF socket shipping		1	$2.54	$2.54
			Total Cost w/ Shipping	$181.02
					Shipping Costs	$41.31

## Sheet2
		MicroComputer Design

Item	Supply Voltage	Current Requirments	Website of Part
Processor (PLCC recom.)	5v	1.5 A max	http://www.jameco.com/webapp/wcs/stores/servlet/ProductDisplay?langId=-1&storeId=10001&catalogId=10001&productId=25291
Processor Socket (PLCC recom.)			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=ED56646-ND
CPU Oscillator (8Mhz reco. & can be used for CPLD clock w/o dividing)	5v	23 mA max	http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=SE1707-ND
CPU Oscillator Socket			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=ED56143-ND
CPLD	5v	65 mA max	http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=122-1262-ND
CPLD Socket (PLCC recom.)			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=AE10067-ND
Jtag (6pin)			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=WM6606-ND
DUART	5v	10 mA	http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=568-3527-5-ND
Duart Socket			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=AE10064-ND
Duart CLK (oscillator)			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=X941-ND
RS232 Driver	5v	15uA	http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=MAX233ACPP%2BG36-ND
RS232 Driver Socket			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=ED56203-ND
Supervisory Chip	5v	10mA	http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=MAX694CPA%2B-ND
Super-Chip Socket			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=ED56083-ND
D-Sub connector (serial cable connector)			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=A35107-ND
Ram	5v	150mA	http://www.jameco.com/webapp/wcs/stores/servlet/ProductDisplay?langId=-1&storeId=10001&catalogId=10001&productId=242376&pa=242376PS
Rom	5v	80mA	http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=AT28HC256-70PI-ND
Ram Socket			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=ED56283-ND
Rom Socket			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=ED56286-ND
5v Regulator	7-20VMAX		http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=425-2629-5-ND
ON/OFF switch			http://www.mouser.com/Search/ProductDetail.aspx?qs=iZD9pWtnGRemNKjEFHFHNQ%3d%3d
Reset Button			http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=SW415-ND
PCB Board
Resistors
Capacitors
Total:	5v	1.838 Amps (at most)
capacitive and current loading charts (high and low state) for each IC can be found on the data sheets.

## Sheet3
Item (x = complete)			Symbol	Pattern	Component
Processor			X	n/a	X
Processor Socket			n/a	X	n/a
CPU Oscillator			X	n/a	X
CPU Oscillator Socket			n/a	X	n/a
CPLD			X	n/a	X
CPLD Socket			n/a	X	n/a
Jtag			X	X	X
DUART			X	n/a	X
Duart Socket			N/A	X	n/a
Duart CLK			X	X	X
RS232 Driver			X	n/a	X
RS232 Driver Socket			N/A	X	n/a
Supervisory Chip			X	n/a	X
Super-Chip Socket			N/A	X	n/a
D-Sub connector			X	X	X
Ram			X	n/a	X
Rom			X	n/a	X
Ram Socket			N/A	X	n/a
Rom Socket			N/A	X	n/a
5v Regulator			X	X	X
ON/OFF switch			X	X	X
Reset Button			X	X	X

CAP (capacitors)			X		X
Resistors			X	X(0805)	X
LED			X		X

PCB Board

## TimeSheet
Time Sheet
	Hours (Estimated)
Break	3	Researched and bought CPLD, 68k, CPLD socket from eBay
Week 1	2	Selecting and ordering parts
	2.5	Selecting and ordering parts
	1	Attend Friday Lab Meeting and work on prelim schematic	9.5
Week 2	1	Finish Prelim Schematic, write progress report
	4.5	Completed ALL component selection. Ordered DUART, AC adaptor, serial cables from eBay & Amazon
	2	Switch out some resistors & capacitors, place Mouser and Digikey orders	13
	4.5	Download and draw symbols
	2	Finish drawing symbols
Week 3	2	Begin Schematic – RS232, Reset Debounce, Regulator	18
	9	Work on Schematic
	1	Lab – Talk to josh about block diagram
	1	Explore DUART functionality
	3	Edit schematic (add 80% of testpoints, remove unneeded connections)
	2	Consult Josh during lab regarding schematic, soldering, DUART, work on block diagram
	3	Work on Schematic
	1	Start researching and laying out PCB	20
	6	PCB Layout (assemble busses, connect most chips)	9.5
	5	PCB Layout (route CPLD)
	2	PCB Layout (sync CPLD with schematic, add capacitors)
	3	Add labels, more LEDS
Week 4	2	Edit schematic and PCB; change WE, CE, OE busses
	2.5	Make schematic look good, make CPLD netlist, final schematic export
	2	Lab with Josh, fit components to printout, fix power jack mistake
	1	Add speaker to unused CPLD pin
	1	Verify parts against datasheets
	1	Order board!!!
	1	Begin VHDL code (netlist, UDF file)

Week 5

Week 6	6	Soldering/ Verifying power pins
Week 7	5	Programming VHDL / DL/Installing New Xilinx on Lab Computers
Week 8	3	Figuring out what the CPLD logic should be for read/write cycles.
	6	Installing Xilinx on computer in lab/ Figuring out VHDL basic test code for LEDs
	5	Programming VHDL CPLD Code and some test Code to figure out current
Week 9	0	Projects/Tests in other classes
Week 10	7	Verified 50% of VHDL code // Tested and verified that ROM works with simple NOP program
	11.5	Verified Ram and Rom works in CPLD. Started Monitor program and attemped serial communication.
	9	Fixed Grounding problem with DUART. Achieved successful 2 way Serial communication with the computer, Computer displays a menu now, and echos text
	9	Added messages and error checking for each initial choice (out of 5 choices) Worked on triple output problem. Tried book code but it didn't work for DUART
	8	FINALLY FIXED THE DUART PROBLEM!!! I now have full serial communication with the computer
	4	Programmed input and output routines
Week 11	11.5	Programmed the view memory (debugged software code that didn't work in hardware) // Programmed modify RAM code
	4	Fixed the computer so it could do byte reads. (the CE lines on the RAM were wired together, so I could only do word writes
	6	Programmed the View and modify registers (Option 2)
	10	Programmed Load Program code for S-Records.
	3	Programmed the Run Program command
Total	179	hours

## Sheet5
IV. Project Progress

Task	Progress
Choose parts	Complete
Design Patterns	Complete
Design Symbols	Complete		Hardware Errors Found
Outline Flow Chart	Complete		On-off toggle backwards
Design Schematic	Complete		Didn't label JTAG clearly
Design Board layout	Complete		Used a female serial conector instead of a male connection
Order Parts	Complete		RS232 pattern width to wide on PCB
Order Board	Complete		Had to add a resistor to Supervisor
Assemble board (solder everything on) (2-5 hrs)	Complete		Pin 5 on Serial connector was not grounded
Write VHDL code for board if using CPLD (2-16 hrs)	Complete		ROM CE lines were tied together therefore I could not do Byte writes
Load simple loop program into Rom and test computer board (1-5 hrs)	Complete
Troubleshoot hardware/ get board working (10 – 80 hrs)	Complete		Software
Develop monitor program (20 – 60 hrs)	Complete		The monitor program displays any key I push 3 times instead of just once.
Get serial communication working	Complete		Adding to an Address regester works in simulation but not on hardware
Code for reading/writing RAM	Complete		Simulator clears out upper part of Regester when doing Word or byte moves
Display basic menu and be able to select options	Complete		Hardware doesn't clear the upper part of the register when doing
Develop necessary functions of monitor program.	Complete
Final test day with working hardware and software	Complete

## Digikey
Web ID	Access ID	Salesorder Number	Shipping Method	Payment Method
162836272	55061	49131690	U.S. Postal Service First Class Mail* (order by 8:00 PM CT)	VISA

Shipping Address
First Name	Last Name	Company	Mail Stop	Address Line 1	Address Line 2	City	State	Postal Code	Country	Email Address	Telephone
Chandler	Griscom CPO#1965	LeTourneau University		LeTourneau University	2100 S Mobberly Ave	Longview	TX	75602	USA	cjgriscom@gmail.com	4846835249

Billing Address
First Name	Last Name	Company	Mail Stop	Address Line 1	Address Line 2	City	State	Postal Code	Country	Email Address	Telephone
Chandler	Griscom			9 Country Club Rd.		Coatesville	PA	19320	USA		4846835249

Index	Quantity	Part Number	Description	Customer Reference	Available Quantity	Backorder Quantity	Unit Price USD	Extended Price USD
1	2	AE10059-ND	CONN SOCKET PLCC 68POS TIN		2	0	1.42	2.84
2	2	AE10057-ND	CONN SOCKET PLCC 44POS TIN		2	0	1.02	2.04
3	1	XC1194-ND	OSC XO 80.000MHZ TTL PC PIN		1	0	2.37	2.37
4	1	XC1158-ND	OSC XO 3.6864MHZ HCMOS TTL PC		1	0	2.47	2.47
5	1	A109020-ND	CONN D-SUB PLUG 9POS R/A SOLDER		1	0	1.54	1.54
6	4	SST39SF040-70-4C-PHE-ND	IC FLASH 4MBIT 70NS 32DIP		4	0	1.67	6.68
7	2	1450-1238-5-ND	IC SRAM 4MBIT 12NS 44SOJ		2	0	4.98	9.96
8	2	296-27963-5-ND	IC DUAL RS232 ESD-PROT 16-DIP		2	0	1.37	2.74
9	10	3M9580-ND	SHUNT JUMPER .1" BLACK GOLD		10	0	0.094	0.94
10	1	EJ508A-ND	CONN PWR JACK 2.1X5.5MM SOLDER		1	0	0.85	0.85
11	2	SW415-ND	SWITCH TACTILE SPST-NO 0.05A 24V		2	0	0.76	1.52
12	1	AE11110-ND	IC PLCC SOCKET 84POS TIN		1	0	1.37	1.37
13	1	LT323AT#PBF-ND	IC REG LDO 5V 3A TO220-3		1	0	4.27	4.27
						Subtotal	39.59
						Shipping	unknown
						Estimated Sales Tax	3.27
						Total	unknown