## TimeSheet
Time Sheet
	Hours (Estimated)
Break	3	Researched and bought CPLD, 68k, CPLD socket from eBay
Week 1	2	Selecting and ordering parts
	2.5	Selecting and ordering parts
	1	Attend Friday Lab Meeting and work on prelim schematic	9.5
Week 2	1	Finish Prelim Schematic, write progress report
	4.5	Completed ALL component selection. Ordered DUART, AC adaptor, serial cables from eBay & Amazon
	2	Switch out some resistors & capacitors, place Mouser and Digikey orders	13
	4.5	Download and draw symbols
	2	Finish drawing symbols
Week 3	2	Begin Schematic – RS232, Reset Debounce, Regulator	18
	9	Work on Schematic
	1	Lab – Talk to josh about block diagram
	1	Explore DUART functionality
	3	Edit schematic (add 80% of testpoints, remove unneeded connections)
	2	Consult Josh during lab regarding schematic, soldering, DUART, work on block diagram
	3	Work on Schematic
	1	Start researching and laying out PCB	20
	6	PCB Layout (assemble busses, connect most chips)	9.5
	5	PCB Layout (route CPLD)
	2	PCB Layout (sync CPLD with schematic, add capacitors)
	3	Add labels, more LEDS
Week 4	2	Edit schematic and PCB; change WE, CE, OE busses
	2.5	Make schematic look good, make CPLD netlist, final schematic export
	2	Lab with Josh, fit components to printout, fix power jack mistake
	1	Add speaker to unused CPLD pin
	1	Verify parts against datasheets
	1	Order board!!!
	1	Begin VHDL code (netlist, constraints file)
	3	Work on VHDL (read/write logic)	12
	7	Finish most of VHDL (implemented all chip logic, dtack, interrupts, gpio)
Week 5	0.5	Redo schematic 11x17
	0.5	Go to lab, write progress report
	1	Setup pulseview/sigrok for saleae logic analyser
	0.5	Test logic analyser using 555 timer (success!)
	3	Solder all but RAM
	4	Test VHDL
	5	Get ROM Working
Week 6	5	Debug sporadic issues caused by lack of BGACK
	0.5	Got RAM working!

Week 7
Week 8
Week 9
Week 10
		Started Monitor program and attemped serial communication.
		Fixed Grounding problem with DUART. Achieved successful 2 way Serial communication with the computer, Computer displays a menu now, and echos text
		Added messages and error checking for each initial choice (out of 5 choices) Worked on triple output problem. Tried book code but it didn't work for DUART
		FINALLY FIXED THE DUART PROBLEM!!! I now have full serial communication with the computer
		Programmed input and output routines
Week 11		Programmed the view memory (debugged software code that didn't work in hardware) // Programmed modify RAM code
		Fixed the computer so it could do byte reads. (the CE lines on the RAM were wired together, so I could only do word writes
		Programmed the View and modify registers (Option 2)
		Programmed Load Program code for S-Records.
		Programmed the Run Program command
Total	166.5	hours

## Memory+Interrupts
	A23	A22	A21	A20	MODE				Interrupts	IPL2	IPL1	IPL0	Meaning
F	1	1	1	1	CPLD	GPI/GPO			7	1	1	1	1000Hz Periodic
E	1	1	1	0	CPLD	GPI/GPO			6	1	1	0	DUART
D	1	1	0	1	CPLD	GPI/GPO			5	1	0	1
C	1	1	0	0	CPLD	GPI/GPO			4	1	0	0
B	1	0	1	1	CPLD	GPI/GPO			3	0	1	1
A	1	0	1	0	CPLD	GPI/GPO			2	0	1	0
9	1	0	0	1	CPLD	GPI/GPO			1	0	0	1	Peripheral
8	1	0	0	0	CPLD	GPI/GPO			0	0	0	0	Acquiire data using 555 circuit, duart clock
7	0	1	1	1
6	0	1	1	0			Masks:	Enable/disable speaker, use data pins as interrupt vector, use data pins as buffer
5	0	1	0	1
4	0	1	0	0
3	0	0	1	1	CPLD	CPLD Masks
2	0	0	1	0	DUART	A19-16 used for mode-setting
1	0	0	0	1	RAM			CPLD MASK
0	0	0	0	0	ROM			7	6	5	4	3	2	1	0
								Speaker_En	Reset DUART	GPI_FlowCtrl	GPO_Address	GPO0_CLK	Soft-Reset Storage (firmware testing)

## Parts
Sheet 1: Parts list
Sheet 2: Supply requirements					MicroComputer Design
Sheet 3: Symbol/Pattern/Component Progress					Sample by Dr. kim
Sheet 4: Time Sheet
Sheet 5: Project Progress
Master Parts List
Item	Symbols	Quantity	Price(each)	Price(sum)	Description	Manufacturers Part Number		Website of Part
Processor		5	$2.26	$11.28	68000 CPU 20MHz, 64-pin PLCC	MC68HC000FN20	J	eBay
Sold Processor		1	$(2.00)	$(2.00)	CPU purchased by Brian
Processor Socket		2	$1.42	$2.84	CONN SOCKET PLCC 68POS TIN	AE10059-ND		digikey
CPU Oscillator		1	$2.37	$2.37	OSC XO 80.000MHZ TTL PC PIN	XC1194-ND		digikey
Oscillator Sockets		2	$0.25	$0.50	8-pin dip socket			supply closet
CPLD		2	$8.00	$16.00	IC CPLD 72 MCELL C-TEMP 84-PLCC	XC9572-7PC84C		eBay
CPLD Socket		5	$0.51	$2.56	5x PLCC IC Socket DIP 84 PINS PLCC-84	?		eBay
Jtag	6-pin	3	$0.68	$2.04	Headers & Wire Housings 16CKT VERT HDR	22-28-4161	m	http://www.mouser.com/Search/ProductDetail.aspx?qs=GAPJcf4kvdv3Xd3iPYTA6w%3d%3d
DUART		2	$5.00	$9.99	40-DIP	MC68681L		eBay
Duart Socket		1	$1.02	$1.02	CONN SOCKET PLCC 44POS TIN	AE10057-ND		digikey
Duart CLK		1	$1.88	$1.88	OSC 3.6864 MHZ 5.0V FULL SIZE	XC1158-ND		digikey
RS232 Driver		2	$1.37	$2.74	IC DUAL RS232 ESD-PROT 16-DIP 250kbps	MAX232EIN		digikey	Needs some 1uF caps
RS232 Driver Socket		1	$0.50	$0.50	16-pin dip socket			supply closet
D-Sub connector		1	$1.54	$1.54	CONN D-SUB PLUG 9POS R/A SOLDER	A109020-ND		digikey
Ram		2	$4.98	$9.96	IC SRAM 4MBIT 12NS 44SOJ	AS7C4098A-12JIN		digikey
Rom		4	$1.67	$6.68	IC FLASH 4MBIT 70NS 32DIP	SST39SF040-70-4C		digikey
Rom ZIF Socket		2	$2.49	$4.98	40Pin ZIF ZIP DIP			ebay
5v Regulator		1	$4.27	$4.27	IC REG LDO 5V 3A TO220-3	LT323AT		digikey
ON/OFF switch		2	$1.09	$2.18	Slide Switches MINI SLIDE SWITCH	SLA1200	m	mouser
Reset Button		2	$0.76	$1.52	SWITCH TACT 6MM SMD MOM 160GF	B3S-1000		http://search.digikey.com/scripts/DkSearch/dksus.dll?Detail?name=SW415-ND
LEDs		18	$0.31	$5.63	SMD 3.2X1.6MM LOW CRNT Blue	APT3216LVBC/D	m	http://www.mouser.com/Search/ProductDetail.aspx?qs=7JStj%2fjQ2SEA%252b%2fUbcPiheQ%3d%3d
Resistor 1.0k	Online	100	$0.01	$0.60	SMD 0805 1Kohms 5% AEC-Q200	ERJ-6GEYJ102V	m	mouser
Resistor 4.7k	Online	100	$0.01	$0.60	SMD 0805 4.7Kohms 5% AEC-Q200	ERJ-6GEYJ472V	m	mouser
Capacitor 1 uF	Online	35	$0.04	$1.33	MLCC - SMD/SMT 0805 1uF 16volts X5R 10%	GRM21BR61C105KA01L	m	mouser
Capacitor 22 uF 6.3V	Online	2	$0.24	$0.48	MLCC - SMD/SMT 0805 22uF 6.3volts X5R 20%	GRM21BR60J226ME39L	m	mouser
Capacitor 47 uF 25V		1	$0.99	$0.99	Ceramic Leaded 47uF 25volts X5R 20% Radial ThruHole	FG16X5R1E476MRT00	m	mouser
Barrel Plug (Male)		1	$0.85	$0.85	CONN PWR JACK 2.1X5.5MM SOLDER	EJ508A-ND		digikey
9V AC Adaptor		1	$6.59	$6.59	9V 2A 2000mA DC AC Adapter Charger	-		ebay
Logic Analyser		1	$6.79	$6.79
PCB Board		1	$33.00	$33.00
PCB Shipping and H		1	$22.00	$22.00
Digikey Shipping		1	$10.55	$10.55
Mouser Shipping+Tax		1	$7.77	$7.77
68000 Shipping		1	$2.00	$2.00
DUART Shipping		1	$2.50	$2.50
CPLD Shipping		1	$4.10	$4.10
84pin socket shipping		1	$1.85	$1.85
ZIF socket shipping		1	$2.54	$2.54
			Total Cost w/ Shipping	$181.02
					Shipping Costs	$41.31

## Digikey
Web ID	Access ID	Salesorder Number	Shipping Method	Payment Method
162836272	55061	49131690	U.S. Postal Service First Class Mail* (order by 8:00 PM CT)	VISA

Shipping Address
First Name	Last Name	Company	Mail Stop	Address Line 1	Address Line 2	City	State	Postal Code	Country	Email Address	Telephone
Chandler	Griscom CPO#1965	LeTourneau University		LeTourneau University	2100 S Mobberly Ave	Longview	TX	75602	USA	cjgriscom@gmail.com	4846835249

Billing Address
First Name	Last Name	Company	Mail Stop	Address Line 1	Address Line 2	City	State	Postal Code	Country	Email Address	Telephone
Chandler	Griscom			9 Country Club Rd.		Coatesville	PA	19320	USA		4846835249

Index	Quantity	Part Number	Description	Customer Reference	Available Quantity	Backorder Quantity	Unit Price USD	Extended Price USD
1	2	AE10059-ND	CONN SOCKET PLCC 68POS TIN		2	0	1.42	2.84
2	2	AE10057-ND	CONN SOCKET PLCC 44POS TIN		2	0	1.02	2.04
3	1	XC1194-ND	OSC XO 80.000MHZ TTL PC PIN		1	0	2.37	2.37
4	1	XC1158-ND	OSC XO 3.6864MHZ HCMOS TTL PC		1	0	2.47	2.47
5	1	A109020-ND	CONN D-SUB PLUG 9POS R/A SOLDER		1	0	1.54	1.54
6	4	SST39SF040-70-4C-PHE-ND	IC FLASH 4MBIT 70NS 32DIP		4	0	1.67	6.68
7	2	1450-1238-5-ND	IC SRAM 4MBIT 12NS 44SOJ		2	0	4.98	9.96
8	2	296-27963-5-ND	IC DUAL RS232 ESD-PROT 16-DIP		2	0	1.37	2.74
9	10	3M9580-ND	SHUNT JUMPER .1" BLACK GOLD		10	0	0.094	0.94
10	1	EJ508A-ND	CONN PWR JACK 2.1X5.5MM SOLDER		1	0	0.85	0.85
11	2	SW415-ND	SWITCH TACTILE SPST-NO 0.05A 24V		2	0	0.76	1.52
12	1	AE11110-ND	IC PLCC SOCKET 84POS TIN		1	0	1.37	1.37
13	1	LT323AT#PBF-ND	IC REG LDO 5V 3A TO220-3		1	0	4.27	4.27
						Subtotal	39.59
						Shipping	unknown
						Estimated Sales Tax	3.27
						Total	unknown

## Clock Calculations
note	FREQ	div value	beat(Hz)	bits			Freq	Code	Bits	<---					Freq	Code	Bits
C0	16.35					8MHz	8000000			Reference Clock			Reference Clock		8MHz	8000000
C#0/Db0	17.32					8888888.88888889			40000000			40000000
D0	18.35					10000000					10000000
D#0/Eb0	19.45					11428571.4285714
E0	20.6					13333333.3333333					13333333.3333333
F0	21.83					16000000
F#0/Gb0	23.12					20000000					20000000
G0	24.5					26666666.6666667
G#0/Ab0	25.96					40000000					Interrupt generator				40000000
A0	27.5					80000000
A#0/Bb0	29.14					Reference Clock (CPU / 2)
B0	30.87					8000000
C1	32.7					\/\/\/
C#1/Db1	34.65
D1	36.71
D#1/Eb1	38.89					<---	Reference Clock					1000
E1	41.2					16000000
F1	43.65
F#1/Gb1	46.25
G1	49
G#1/Ab1	51.91
A1	55
A#1/Bb1	58.27
B1	61.74
C2	65.41
C#2/Db2	69.3
D2	73.42
D#2/Eb2	77.78
E2	82.41
F2	87.31
F#2/Gb2	92.5
G2	98
G#2/Ab2	103.83
A2	110
A#2/Bb2	116.54
B2	123.47
C3	130.81
C#3/Db3	138.59
D3	146.83
D#3/Eb3	155.56
E3	164.81
F3	174.61
F#3/Gb3	185
G3	196
G#3/Ab3	207.65
A3	220
A#3/Bb3	233.08
B3	246.94
C4	261.63
C#4/Db4	277.18
D4	293.66
D#4/Eb4	311.13
E4	329.63
F4	349.23
F#4/Gb4	369.99
G4	392
G#4/Ab4	415.3
A4	440
A#4/Bb4	466.16
B4	493.88
C5	523.25
C#5/Db5	554.37
D5	587.33
D#5/Eb5	622.25
E5	659.25
F5	698.46
F#5/Gb5	739.99
G5	783.99
G#5/Ab5	830.61
A5	880
A#5/Bb5	932.33
B5	987.77
C6	1046.5
C#6/Db6	1108.73
D6	1174.66
D#6/Eb6	1244.51
E6	1318.51
F6	1396.91
F#6/Gb6	1479.98
G6	1567.98
G#6/Ab6	1661.22
A6	1760
A#6/Bb6	1864.66
B6	1975.53
C7	2093
C#7/Db7	2217.46
D7	2349.32
D#7/Eb7	2489.02
E7	2637.02
F7	2793.83
F#7/Gb7	2959.96
G7	3135.96
G#7/Ab7	3322.44
A7	3520
A#7/Bb7	3729.31
B7	3951.07
C8	4186.01
C#8/Db8	4434.92
D8	4698.63
D#8/Eb8	4978.03
E8	5274.04
F8	5587.65
F#8/Gb8	5919.91
G8	6271.93
G#8/Ab8	6644.88
A8	7040
A#8/Bb8	7458.62
B8	7902.13